## Summary
KGF Black Pepper Procurement 2026 - Verstegen Commitment
Prepared for Verstegen. Volumes in metric tons (MT). Update the Purchase Log; this page recalculates.
Metric | Value | Unit | Basis
Commitment to Verstegen | 100 | MT | Contracted volume for the 2026 season
Procured to date |  | MT | Live total from the Purchase Log
Remaining to procure |  | MT | Commitment less procured
Procurement weeks remaining |  | weeks | Counted from the current week to end November
Required run rate |  | MT/week | Remaining divided by weeks remaining
Current agreed target | 3 | MT/week | Minimum agreed with Ira
Run-rate gap |  | MT/week | Required less current target
Why the run rate matters
The minimum of 3 MT per week agreed with Ira does not reach 100 MT within the season. At 3 MT per week over the remaining weeks the season lands well short of the commitment. The Required run rate cell above is the number that has to be met, and the Weekly Plan tab is where it is allocated by area, team and collector.
Quality specification
Parameter | Target | Latest observed | Source
Grade | ASTA 550 |  | Verstegen contract
Bulk density | >= 520 g/l | 520 g/l | Deni lot, self-reported
Moisture content | <= 14% | 18% | Deni lot, self-reported, no photo evidence
Light berries | Minimise | High share, early harvest | Field observation

## Weekly Plan
Weekly Procurement Plan - objective, area, team, collector
Structure requested by Evert-Jan. Fill Objective before the week starts; Actual pulls from the Purchase Log automatically.
Week | Week start | Week end | Objective (MT) | Actual (MT) | Variance (MT) | Area | Team / PIC | Collector / Source | Target price (IDR/kg) | Status | Notes
W1 | 2026-08-17 | 2026-08-23 | 5 |  |  | Tanggamus, Pesawaran, Lampung Barat, Lampung Utara | Rafiq, Widy, Nico, Teguh | Deni (3.7 MT to Tekad); 8 farmers Tanggamus (1 MT); Lampung Utara (new) | 102000 | In progress | Lampung Utara is a new source, first visit this week. Nico and Widy to go.
W2 | 2026-08-24 | 2026-08-30 | [7 empty] | Planned
W3 | 2026-08-31 | 2026-09-06 | [7 empty] | Planned
W4 | 2026-09-07 | 2026-09-13 | [7 empty] | Planned
W5 | 2026-09-14 | 2026-09-20 | [7 empty] | Planned
W6 | 2026-09-21 | 2026-09-27 | [7 empty] | Planned
W7 | 2026-09-28 | 2026-10-04 | [7 empty] | Planned
W8 | 2026-10-05 | 2026-10-11 | [7 empty] | Planned
W9 | 2026-10-12 | 2026-10-18 | [7 empty] | Planned
W10 | 2026-10-19 | 2026-10-25 | [7 empty] | Planned
W11 | 2026-10-26 | 2026-11-01 | [7 empty] | Planned
W12 | 2026-11-02 | 2026-11-08 | [7 empty] | Planned
W13 | 2026-11-09 | 2026-11-15 | [7 empty] | Planned
W14 | 2026-11-16 | 2026-11-22 | [7 empty] | Planned
W15 | 2026-11-23 | 2026-11-29 | [7 empty] | Planned
TOTAL

## Purchase Log
Purchase Log - one row per lot received
This is the single source of truth. Weekly Plan and Summary read from it. Volume in kg. Attach the density and moisture reading for every lot.
Date | Lot ID | Source type | Supplier / Farmer name | Area | Volume (kg) | Price (IDR/kg) | Value (IDR) | Moisture (%) | Density (g/l) | Quality OK | Evidence (photo/video) | PIC | Notes
2026-08-12 | L-001 | Collector | Deni | Tanggamus / Lampung Barat border | 2211 | 102000 | [5 empty] | Rafiq | Carried over from report to 12 Aug
2026-08-12 | L-002 | Farmer | 19 farmers (see 12 Aug report) | Tanggamus / Pesawaran | 2192.3 | [5 empty] | Procurement report 12 Aug | Widy | Aggregate of 19 farmer purchases

## Processing & Shipment
Processing and Shipment - drying, cleaning, grading, dispatch
Cleaning and grading start at the 8 MT threshold set by VSA. Drying can run before that.
Batch | Date in | Raw volume (kg) | Process | Date out | Output volume (kg) | Yield (%) | Moisture out (%) | Density out (g/l) | Grade achieved | Shipment date | Destination

## Reference
Reference - team, sources, prices, reporting commitments
Team and area assignment
Name | Role | Area / responsibility
Muhammad Rafiq | Technical Manager | Overall field coordination, Tanggamus
Widyanto (Pak Widy) | Procurement | Farmer and collector purchasing, Air Hitam
Nico Setyo Utomo | Data Management | Lampung Utara source development, traceability
Teguh | Source contact | Additional collector source, to be confirmed
Heri Adi Prasetyo | Operational Manager | Field operations and farmer coordination
Sources and indicative prices
Source | Type | Delivery point | Price (IDR/kg) | Reliability
Deni | Collector | Tekad buying station | 102000 | Reliable so far
Lampung Utara source | Collector | Kotabumi | 100000 | New, first visit this week
Tanggamus farmers | Farmer | VH Sirna Galih / Tekad |  | aGROWforests binaan
Pesawaran farmers | Farmer | Pesawaran |  | aGROWforests binaan
Reporting commitments to Verstegen
Item | Frequency | Channel | Content | Owner
Procurement update | Daily | WhatsApp | Plan for the day, previous day activity, volumes, names | Rafiq
Weekly overview | Weekly | Email | Progress against the weekly objective, variance, next week plan | Arif
Quality evidence | Per lot | WhatsApp | Photo and short video of density and moisture check at farm level | Widy / Nico
Production schedule | On request | Email | Cleaning and grading schedule | Rafiq